## DCIP Cover Page
LEA Name: | Port Jervis City School District | ENTER DATA INTO ALL YELLOW CELLS.
BEDS Code: | 441800050000
2018-2019 District Comprehensive Improvement Plan (DCIP)
Contact Name | Nick Pantaleone | Title | Assistant Superintendent for Instruction
Phone | 845-858-3100 ext. 15521 | Email | npantaleone@pjschools.org
Website for Published Plan | www.pjschools.org
APPROVAL OF THIS PLAN BY THE SUPERINTENDENT AND BOARD OF EDUCATION (IN NEW YORK CITY, THE CHANCELLOR OR THE CHANCELLOR’S DESIGNEE) IS MANDATORY.
Implementation is required no later than the first day of regular student attendance.
Signatures confirm the respective parties certify that the DCIP addresses all of the required components of the ESSA and Commissioner's Regulations as detailed on page 1 of this document and understand that any significant modification of the school district’s approved plan require the prior approval of the commissioner.
THE SIGNATURES BELOW CONFIRM APPROVAL.
Position | Signature | Print Name | Date
Superintendent | Mike Rydell | Mike Rydell | 2018-09-18
President B.O.E. | Tanya Parker-Hughes | Tanya Parker-Hughes | 2018-09-18

## Assurances
Statement of Assurances
By signing this document, the Local Education Agency certifies that:
x | 1. The District Comprehensive Improvement Plan (DCIP) has been developed in consultation with parents, school staff and others in accordance with the requirements of Shared-Decision Making (CR 100.11) to provide a meaningful opportunity for stakeholders to participate in the development of the plan and comment on the plans before they are approved.
x | 2. The District Comprehensive Improvement Plan (DCIP) has been formally approved by the school board and will be made widely available through public means, such as posting on the Internet, distribution through the media and distribution through public agencies.
x | 3. The District Comprehensive Improvement Plan (DCIP) will be implemented no later than the beginning of the first day of regular student attendance.
x | 4. A comprehensive systems approach will be established to recruit, develop, retain and equitably distribute effective teachers and school leaders as part of the implementation of the Annual Professional Performance Review (APPR) system required by Education law §3012(c) and §3012(d).
x | 5. Professional development will be provided to teachers and school leaders that will fully support the strategic efforts described within this plan.
x | 6.Meaningful time for collaboration will be used to review and analyze data in order to inform and improve district policies, procedures, and instructional practices.

## District Leadership Team
District Leadership Team
DISTRICT LEADERSHIP TEAM: The DCIP must be developed in consultation with parents, school staff, and others pursuant to §100.11 of Commissioner’s Regulations. Participants who are regularly involved in your district and school improvement initiatives, such as community organizations or institutes of higher education should be included. By signing below, stakeholders ascertain that, although they may not agree with all components of the plan, they have actively participated in the development and revision of the DCIP.
Instructions: List the stakeholders who participated in developing the DCIP as required by Commissioner’s Regulations §100.18. Provide dates and locations of Local Stakeholder meetings. Boxes should be added as necessary.
Meeting Date(s) | Locations(s) | Meeting Date(s) | Location(s)
2017-12-11 | ASK Library
2018-01-29 | HBE Library
2018-02-28 | HS Library
2018-03-21 | MS Library
2018-04-09 | HS Library
Name | Title / Organization |  | Signature
Mike Rydell | Superintendent |  | Mike Rydell
Nick Pantaleone | Assistant Superintendent for Instruction |  | Nick Pantaleone
Meagan Sullivan | Director of Pupil Personnel |  | Meagan Sullivan
Jean Lain | Middle School Principal |  | Jean Lain
Anthony Lazzaro | Middle School Assistant Principal |  | Anthony Lazzaro
Brett Cancredi | ASK Principal |  | Brett Cancredi
Jared Kahmar | HBE Principal |  | Jared Kahmar
Dr. Deana Stevenson | Consultant/PLC Associates Facilitator |  | Dr. Deana Stevenson

## Overview
| DCIP Plan Overview | REVIEWER FEEDBACK
In this section, the district must describe the development of the plan, the degree to which the previous school year's DCIP was successfully implemented, overall improvement mission or guiding principles at the core of the strategy for executing the mission/guiding principles, the key design elements of the DCIP, and other unique characteristics of the plan (if any), and provide evidence of the district’s capacity to effectively oversee and manage the improvement plan.
The DCIP must be made widely available through public means, such as posting on the Internet, by the district. The Overview will serve as the at-a-glance summary of how the district will use various funding sources to improve student achievement. A complete overview will address the following:
1. Rate the degree to which the District achieved the goals identified in the previous year's District Comprehensive Improvement Plan (Mark with an "X").
Limited Degree (Fewer than 20% of goals were achieved.)
Partial Degree (Fewer than 50% of goals were achieved.)
x | Moderate Degree (At least 50% of goals were achieved.)
Major Degree (At least 90% of goals were achieved.)
2. Rate the degree to which the District successfully implemented the activities identified in the previous year's DCIP (Mark with an "X").
Limited Degree (Fewer than 20% of activities were carried out.)
Partial Degree (Fewer than 50% of activities were carried out.)
x | Moderate Degree (At least 50% of activities were carried out.)
Major Degree (At least 90% of activities were carried out.)
3. Rate the degree to which the activities identified in the previous year's District Comprehensive Improvement Plan impacted academic achievement targets for identified subgroups (Mark with an "X").
Limited Degree (No identified subgroups improved achievement.)
Partial Degree (Some of the identified subgroups improved achievement.)
x | Moderate Degree (A majority of identified subgroups improved achievement.)
Major Degree (All identified subgroups improved achievement.)
4. Rate the degree to which the activities identified in the previous year's DCIP increased Parent Engagement (Mark with an "X").
Limited Degree (There was no increase in the level of Parent Engagement.)
Partial Degree (There was a minor increase in the level of Parent Engagement.)
Moderate Degree (There was modest increase in the level of Parent Engagement.)
x | Major Degree (There was a significant increase in the level of Parent Engagement.)
5. Rate the degree to which the activities identified in the previous year's District Comprehensive Improvement Plan received the funding necessary to achieve the corresponding goals (Mark with an "X").
Limited Degree (Fewer than 20% of planned activities were funded.)
x | Partial Degree (Fewer than 50% of planned activities were funded.)
Moderate Degree (At least 50% of planned activities were funded.)
Major Degree (At least 90% of planned activities were funded.)
6. Identify in which Tenet the district made the most growth during the previous year (Mark with an "X").
Tenet 1: District Leadership and Capacity
Tenet 2: School Leader Practices and Decisions
x | Tenet 3: Curriculum Development and Support
Tenet 4: Teacher Practices and Decisions
Tenet 5: Student Social and Emotional Developmental Health
Tenet 6: Family and Community Engagement
7. Identify in which Tenet identified schools made the most growth during the previous year (Mark with an "X").
Tenet 1: District Leadership and Capacity
x | Tenet 2: School Leader Practices and Decisions
Tenet 3: Curriculum Development and Support
Tenet 4: Teacher Practices and Decisions
Tenet 5: Student Social and Emotional Developmental Health
Tenet 6: Family and Community Engagement
In reflecting on the PREVIOUS YEAR'S PLAN:
• Describe the most significant positive impact(s) that resulted from the previous year’s plan (may include such examples as specific changes in adult behavior and/or measurable changes in student outcomes).
Increase in parent engagement; increase in graduation rate and improved feedback loop for teacher evaluations.
• Describe all mid-course corrections to the previous year’s plan in response to data review and needed adjustment. Include details of current impact and expectations for sustainability moving forward.
Increase communication modalities to parents and stakeholders; increase utilization of student specific data and benchmarking to improve instructional planning.
In developing the CURRENT YEAR'S plan:
• List the highlights of the improvement initiatives described in the current DCIP.
100% of all school leaders will review their school's data dashboards with the District leadership, in order to monitor the progress of each of the school's SMART Goals related to the key District and school initiatives: involving teacher practice, student engagement and student achievement. In addition, implement a K-12 cohesive RtI plan. Also, create professional development opportunities focused on instructional look fors for our teachers and school leaders.
• List the identified needs in the district that will be targeted for improvement in this plan.
The District will target the areas of teacher practice, student engagement, and student achievement within this plan. In addition, implement a K-12 cohesive RtI plan.
• State the mission or guiding principles of the district and describe the relationship between the mission or guiding principles and the identified needs of the district.
"The Port Jervis City School District, in partnership with our community, has an uncompromising commitment to measurably improve student achievement and prepare students to be productive and responsible life-long learners, ready to meet the challenges of citizenship in our ever-changing global society." The mission and the plans of the DCIP will allow for continued growth in the realms of student and family engagement, student social and emotional health, academic achievement, and character education.
• List the student academic achievement targets for the identified subgroups in the current plan.
The goal for the economically disadvantaged subgroup is from the current 74 to the New York cut score of 5%. The goals for the special education subgroup is from the current 39.5 to5%.
• Describe how organizational structures will drive strategic implementation of the mission/guiding principles.
The District will continue to monitor progress using a data dashboard and benchmarking for all students. A strategic plan initiative will commence in the fall of 2018 and progress throughout the year to further aid in realizing District SMART Goals.
• List anticipated barriers that may impact the ability to accomplish the mission or guiding principles and how those barriers will be addressed.
School leaders recognize the importance of the continuing to foster the home to school connection and continuing to motivate students to increase aspirations.
• Describe the professional development opportunities that will be provided to teachers and school leaders and the rationale for each opportunity.
Professional development will be provided to administrators to further improve classroom observations and the feedback loop. Professional development, student presentations, and student engagement will include social and emotional health topics as well as those focused on curriculum and planning decision making.
• List all methods of dialogue that district leaders will implement to strengthen relationships with school staff and the community.
District website, email, collaborative parent meetings, social media, and a district-specific communication application.
• List all the ways in which the current plan will be made widely available to the public.
District website, parent forums, social media, and a district-specific communication application.

## Tenet 1
Tenet 1: District Leadership and Capacity |  |  | REVIEWER FEEDBACK
Tenet 1: District Leadership and Capacity |  | The district examines school systems and makes intentional decisions to identify and provide critical expectations, supports and structures in all areas of need so that schools are able to respond to their community and ensure that all students are successful. | #NAME?
B1. Most Recent DTSDE Review Date: |  | 2018-09-01
B2. DTSDE Review Type: |  | DCIP Planning Document
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | Of the District's 4 schools, the middle school is the Focus School. The middle school had a DTSDE District-Led Support Visit this spring. During the visit, the team identified the need for an effective monitoring and data collection system in many areas including: lesson plans, regular learning walks, curriculum monitoring data for ELA and math, STAR assessment data, and SEDH monitoring data in order for the District and building leaders to make decisions. Data from all of these areas is in beginning stages of being organized, collected, analyzed, and shared with building leaders through the District Cabinet in a "closed loop system" - meaning data is utilized in a way that changes and improves practices. This data also should be utilized to inform professional development that addresses global areas of focus as well as differentiated by building in order for there to be progress toward achieving District achievement targets. There is a need for the District to monitor building-level data from the various teams (curriculum, instruction, assessment, SEDH) in order to ensure that the data collected is being analyzed and used to inform all building-level decisions. Fidelity of practice is a need.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, the District will implement a fully operationalized data system to monitor all the District-level systems (curriculum, instruction, assessment, and SEDH), in order to make decisions to support the fidelity of implementation of District priorities and provide support to building leaders to reach student achievement targets. Evidence for this fully operationalized system will include agendas, documented data charts and reports, from both internal stakeholders and participating partners external to the District, verifying the implementation of this high accountability infrastructure.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Monitoring system for DCIP/SCEP implementation Student Average Daily Attendance Student Drop-Out Rate Student Credit Accruals (HS students) Submission of reports aligned to data cycles by internal staff and external partners
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-18 | 2018-06-19 | The Superintendent and Assistant Superintendent will use the District Strategic Plan, aligned to the action planning identified in the DCIP to monitor progress toward the implementation of the actions identified in the Strategic Plan Responsible: Superintendent and Assistant Superintendent Participants: Superintendent and Assistant Superintendent Frequency: Monthly Intended Outcome: To ensure systematic, consistent monitoring of all data systems and DCIP action plans in service to the operationalizing of the District Strategic Plan and DCIP.
2018-09-18 | 2018-06-19 | District Assistant Superintendent will monitor a quarterly report from middle school leaders that compiles data on completion of SCEP action plans and progress toward meeting the goals for Tenets 2-6. These reports will include: quarterly report card data, attendance, disciplinary and SEDH data that includes sub-group disaggregation Responsible: Assistant Superintendent Participants: Middle School Leaders Frequency: Quarterly Intended Impact: District Cabinet will monitor progress in order to inform their actions and provide support.
2018-09-18 | 2018-09-18 | District Assistant Superintendents will create a schedule of meetings for review of data and identify a data review cycle to monitor all data systems identified in the goal Responsible: Assistant Superintendent Participants: Assistant Superintendent Frequency: Once Intended Outcome: To ensure systematic, consistent review of all data systems identified in the goal.
2018-09-18 | 2018-06-19 | The Superintendent, Assistant Superintendent for Curriculum and Instruction and school leaders will collect consistent quantitative baseline data for the District every 5-weeks to measure progress in standing agenda items: academic performance, curricular/lesson planning, walk-through findings, RtI intervention, attendance, SEDH (including student behavior), and parental/community concerns in order for the Superintendent and Board of Education monitoring of whole District data to inform their decision-making and budgetary development Responsible: Assistant Superintendent Participants: Assistant Superintendent, building leaders, leadership teams and District Cabinet Frequency: Ongoing Intended Outcome: To progress monitor indicators that will inform decision-making.
2018-09-18 | 2018-06-19 | District Assistant Superintendent will create a process and protocol for the analysis of data during Principal Cabinet meetings Responsible: Assistant Superintendent Participants: Assistant Superintendent, Cabinet leaders, building leaders and leadership teams Frequency: Monthly Intended Outcome: To ensure a systematic, commonly understood process for analysis, monitoring and decision-making regarding building-level data.
2018-09-18 | 2018-09-18 | District Assistant Superintendent will provide training in data-driven instructional protocols to be used in monthly Principals' Meetings so data is consistently analyzed, monitored and used to make decisions to support the implementation of District initiatives Responsible: Assistant Superintendent Participants: Assistant Superintendent, Cabinet leaders, building leaders and leadership teams Frequency: Monthly Intended Outcome: To ensure that all building leaders and leadership teams are using data to identify gaps in the implementation of District initiatives and to inform decision-making to address those gaps.
2018-09-18 | 2018-06-19 | The Superintendent will require all Cabinet staff to attend the same professional development as school leaders through attendance at the same workshops or through specially targeted PD for Cabinet Responsible: Superintendent Participants: All Cabinet and building leaders Frequency: All scheduled PD Intended Outcome: To increase knowledge of building expectations and practices in order for them to support, monitor and provide feedback to school leaders in implementation of required practices.
2018-09-18 | 2018-06-19 | The Assistant Superintendent will meet with each building principal to monitor building-level data from all systems, progress toward implementation of the SCEP, and implementation with fidelity of District initiatives Responsible: Assistant Superintendent Participants: Assistant Superintendent and building leaders Frequency: Monthly Intended Outcome: To hold buildings accountable for the implementation of District initiatives and the collection and use of building data to monitor and adjust progress toward District-identified goals.
2018-09-18 | 2018-06-19 | Assistant Superintendent will use and analyze the feedback from the PLC Professional Development Reflection Tool on the effectiveness of the targeted professional development to monitor and adjust ongoing professional development Responsible: Assistant Superintendent Participants: Assistant Superintendent, building leaders and leadership teams Frequency: Ongoing Intended Impact: To monitor the implementation of the professional development to ensure its effectiveness and differentiate subsequent professional learning.
2018-04-19 | 2018-05-19 | The District will conduct the follow-up Data Triangle survey with a 90% response rate from staff and students in all buildings to ascertain District Assets Responsible: Assistant Superintendents Participants: All District staff and students Frequency: Once Intended Outcome: To gain stakeholder data at a reliable level to make decisions.
2018-09-18 | 2018-06-19 | The Assistant Superintendent for Curriculum and Instruction and all District consultants will schedule and convene quarterly meetings which will monitor the achievement of DCIP goals and provide feedback, action steps and input into the 2019-2020 DCIP Responsible: Assistant Superintendent Participants: District consultants, Assistant Superintendent Frequency: Quarterly Intended Outcome: To ensure deep implementation of the DCIP.

## Tenet 2
Tenet 2: School Leader Practices and Decisions |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 2.1 - The district works collaboratively with the school to provide opportunities and supports for the school leader to create, develop and nurture a school environment that is responsive to the needs of the entire school community. | SOP 2.1 - The district works collaboratively with the school to provide opportunities and supports for the school leader to create, develop and nurture a school environment that is responsive to the needs of the entire school community.
B1. Most Recent DTSDE Review Date: |  | 2018-09-01
B2. DTSDE Review Type: |  | DCIP Planning Document
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | District student achievement data in schools identified in the New York State Accountability System reveal the need to improve student achievement levels with attention to identified sub-groups. The DTSDE support visits reported that in order for the school leaders to support and improve instructional practices and outcomes in a continuous and sustainable manner for all students, feedback to teachers must be actionable and focused on improving the quality of instruction. This means not merely the presence of the strategy during the lesson, but the verifiable impact. According to the DTSDE support visit, many of the school leaders conceded that while students are engaged in classrooms as noted through the Learning Walk Tool, the level of engagement is not consistently rigorous or at Webb’s Depth of Knowledge Levels 3 and 4. Data gathered from the Learning Walk Tool will have higher impact when utilized as intended with the data being reviewed, analyzed and then as a catalyst to make modifications in instructional practices. Currently, there is a gap in implementing this fully. The DTSDE support visits indicated that there are gaps in understanding by teachers and school leaders of what rigor is and what strategies teachers can use to create rigorous lessons. The current tool is used primarily as a checklist and does not consistently include formative and actionable feedback to teachers, with recommended strategies intended to improve teacher practice. There is a need for the District to support school leaders in their development and implementation of a Learning Walk Tool that is calibrated across school leaders to ensure high expectations and consistent implementation of District initiatives.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, 100% of building leaders will use the District-designed Learning Walk Tool with the frequency of 80/month, 20/week and 5/day (minimally - larger leadership teams and schools should go beyond this) to gather and use data around District-identified instructional practices and curriculum implementation to ensure high expectations through the consistent implementation of District initiatives.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Current curriculum implementation maps/rubrics Learning Walk data Leveraged Leadership Inventory
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
Sept. 2018 | October.2018 | The Assistant Superintendent will meet to review the Learning Walk Tool and ensure that the tool can functionally meet the key instructional practices identified by the District, including the quality of the implementation of the practice Responsible: Assistant Superintendent Participants: Assistant Superintendent and school leaders Frequency: Ongoing Intended Impact: To ensure the tool is able to capture the necessary data identified by the District for classroom practices and curriculum implementation and indicate the quality of these practices. Data will be analyzed at the District and school levels.
2018-09-18 | 2018-05-19 | The Principals' Cabinet will meet to develop a common understanding of what the Look-Fors are and the quality of the practice that these Look Fors reflect in classroom instruction Responsible: Assistant Superintendent Participants: Assistant Superintendent and building leaders and leadership teams Frequency: Ongoing Intended Outcome: To calibrate the understanding of the instructional practices identified in the Learning Walk Tool.
2018-09-18 | 2018-05-19 | Using the Danielson rubric, provide school leaders with professional development that supports a common understanding of the quality of implementation of the Look Fors identified in the Learning Walk Tool Responsible: Assistant Superintendent Participants: Assistant Superintendent, building leaders and leadership teams Frequency: Ongoing Intended Outcome: To calibrate the understanding of the quality of implementation of the instructional practices.
2018-09-18 | 2018-06-19 | The District Cabinet will conduct building Learning Walks with school leaders to assess the level of implementation of the Learning Walk Tool and progress monitor the level of implementation of the District initiatives around classroom practices and curriculum Responsible: Superintendent Participants: District Cabinet members, building leaders Intended Outcome: To assess the extent and level of implementation of District identified initiatives and to provide feedback to building leaders.
2018-09-18 | 2018-06-19 | Using the identified Leveraged Leadership Inventory indicators (#1, 2, 5, 11 and 13), the Assistant Superintendent will determine the strengths of building leaders to provide teachers with timely, actionable feedback to support implementation of District initiatives regarding instructional practices Responsible: Assistant Superintendent Participants: Assistant Superintendent Frequency: Monthly Intended Outcome: To hold building leaders accountable for leadership behaviors that support teacher improvement in instructional practice.

## Tenet 3
Tenet 3: Curriculum Development and Support |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 3.1 - The district works collaboratively with the school(s) to ensure CCLS curriculum that provide 21st Century and College and Career Readiness skills in all content areas and provides fiscal and human resources for implementation. | SOP 3.1 - The district works collaboratively with the school(s) to ensure CCLS curriculum that provide 21st Century and College and Career Readiness skills in all content areas and provides fiscal and human resources for implementation.
B1. Most Recent DTSDE Review Date: |  | 2018-09-01
B2. DTSDE Review Type: |  | DCIP Planning Document
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | At all levels and particularly at the secondary level, there continues to be inconsistent implementation of curriculum of the identified areas. At the elementary level, building leaders and teachers have received professional development around the District instructional Look-Fors (Learning Targets, Higher Order Questions, Student Engagement, Checks for Understanding, and Differentiated Instruction). Learning Walks have been done by consultants from PLC Associates and building leaders to monitor the implementation of the modules and the professional development. There continues to be inconsistencies across the District in implementation of the curriculum including pacing and level of rigor. The DTSDE support visits and SCEPs reflect the need for timely, actionable feedback on teacher lesson planning. The current lesson planning does not reflect rigorous expectations aligned to the expectations of the CCLS for all students because all teachers are not receiving and acting on timely, actionable feedback. There is a need for the District to monitor the implementation of curriculum more closely in all content areas and to provide feedback to building leaders to ensure a guaranteed, viable curriculum that is vertically aligned for all students.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, the Assistant Superintendent for Curriculum and Instruction will monitor the implementation of the identified curricula (Math, Science, ELA and Social Studies) so that 100% of the buildings will operationalize these guaranteed, viable curriculums with fidelity for all students, measured by content specific rubrics.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Current curriculum implementation maps/rubrics Common Lesson planning elements Learning Walk data focused on curriculum monitoring
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-18 | 2018-10-18 | District leaders will work with school leaders, by band (K-3, 4-6, 7-8, and 9-12), during summer weeks to populate an instructional schedule template reflecting curriculum expectations Responsible: District leaders Participants: Building leaders Frequency: Several meetings Intended Outcome: shared understanding of curriculum pacing.
2018-09-18 | 2018-06-19 | Assistant Superintendent of Curriculum and Instruction and K-8 Building leaders will work collaboratively to design continued professional learning opportunities supporting the implementation of ELA and mathematics curriculum Responsible: Assistant Superintendent and K-8 Building Leaders Participants: K-8 Building leaders and teachers Frequency: Ongoing Intended Outcome: To strengthen teacher content knowledge and content pedagogy to ensure the implementation with fidelity.
Sept.2018 | Oct.2018 | Assistant Superintendent of Curriculum and Instruction and K-8 Building leader will create and share with teachers a K-8 ELA and mathematics curriculum calendar that paces the curriculum to include: monthly module and skill expectations, common interim assessments, and professional development supports Responsible: Assistant Superintendent, K-8 Building Principals Participants: Assistant Superintendent, K-8 Building Principals Frequency: Several meetings Intended Outcome: To ensure that the curriculum is implemented with fidelity across the district.
Sept.2018 | Oct.2018 | Assistant Superintendent of Curriculum and Instruction and K-8 Building Leaders will schedule science curriculum writing leading to state exams to plan instruction that links science standards to learning targets and lesson tasks for increased student achievement Responsible: Assistant Superintendent and K-8 building leaders Participants: Assistant Superintendent, K-8 building leaders Frequency: Once Intended Outcome: To write science curriculum aligned to the NGSS and that supports lesson planning.
2018-09-18 | 2018-01-19 | Assistant Superintendent of Curriculum and Instruction will present the completed science curriculum maps to the Superintendent for approval and District-wide distribution Responsible: Assistant Superintendent Participants: Superintendent, Assistant Superintendent, Cabinet Frequency: Once Intended Outcome: The Science curriculum will be approved for implementation across the District.
2018-01-19 | 2018-05-19 | Assistant Superintendent of Curriculum and Instruction and K-8 Building Leaders will work collaboratively to design professional development to support implementation of the science curriculum Responsible: Assistant Superintendent Participants: K-8 Building leaders, teacher leaders, teachers Frequency: Ongoing Intended Outcome: To support the fidelity of implementation of the science curriculum.
2018-01-19 | 2018-06-19 | Assistant Superintendent with the building leadership teams will monitor implementation of the Science curriculum through the use of the Learning Walk Tool, monthly Science department meetings, and monthly meetings with the building leaders and Assistant Superintendent Responsible: Assistant Superintendent, building leaders, Science teacher leaders Participants: Assistant Superintendent, building leaders, Science teacher leaders Frequency: Monthly Intended Outcome: To ensure implementation with fidelity of the science curriculum across the District.
2018-09-18 | 2018-05-19 | Assistant Superintendent will design and lead professional development in curriculum writing expectations Responsible: Assistant Superintendent Participants: Science Department leaders and teachers Frequency: Ongoing Intended Outcome: To ensure a high-quality curriculum is written.
2018-09-18 | 2018-05-19 | Assistant Superintendent and High School Building Leaders will schedule monthly curriculum writing leading to the respective Regents examinations to enhance the Science, Mathematics, and Social Studies curriculum maps Responsible: Assistant Superintendent and High School building leaders Participants: Assistant Superintendent, department leaders and teachers Intended Outcome: All students have access to a guaranteed, viable curriculum and receive planned instruction that links content standards to learning targets and lesson tasks for increased student achievement.
2018-09-18 | 2018-02-19 | Assistant Superintendent will present the completed curriculum maps to the Superintendent for approval and district-wide distribution. Responsible: Assistant Superintendent Participants: Superintendent, Assistant Superintendent, Cabinet Frequency: Once Intended Outcome: The Science curriculum will be approved for implementation across the district.
2018-01-19 | 2018-05-19 | Assistant Superintendent and High School Building Leaders will work collaboratively to design professional development to support implementation of the curriculum maps in Rubicon Atlas with principals and teachers. Responsible: Assistant Superintendent Participants: High School Building Leaders, Teacher Leaders, Teachers Frequency: Ongoing Intended Outcome: To support the fidelity of implementation of the science curriculum.
2018-09-18 | Ape 19 | Professional development for school leaders and district administration in a consistent district-wide protocol for analysis of data that will identify curriculum gaps and inform curricula decision-making. Responsible: District Administration and District consultants Participants: District administration and Building leaders Frequency: ongoing Intended Outcome: to increase skill set in data analysis for monitoring and adjusting curriculum implementation.
Sept.2018 | Oct.2018 | Assistant Superintendent working with building leaders will create a common lesson feedback form Responsible: Assistant Superintendent and building leaders Participants: Assistant Superintendent and building leaders Frequency: Once Intended Outcome: To create a common form that provides a common approach to and consistent feedback to teacher lesson plans.
2018-09-18 | 2018-11-18 | The District will provide professional development to building leaders on the use of an identified protocol for analyzing student work. This protocol will be shared with all faculties in order to support their instructional decision-making during PLC meetings Responsible: Assistant Superintendent Participants: Building leaders and leadership teams Frequency: 2-3 sessions Intended Outcome: To develop the leaders' skill set in gathering evidence of student learning against intended curriculum outcomes.
2018-09-18 | 2018-05-19 | Assistant Superintendent will monitor the school's collection and analysis of data (curriculum-based measures and local assessment) Responsible: Assistant Superintendent Participants: Building leaders and Assistant Superintendent Frequency: Monthly Intended Outcome: To ensure that the buildings are using the data to identify curriculum gaps in order to adjust and monitor the curriculum so that it is being implemented with fidelity.
2018-09-18 | 2018-05-19 | District leaders will monitor principal efforts (#’s 12-15) during monthly Leadership in Action meetings by formalizing the presentation of building goals, data, and progress toward goals Responsible: Assistant Superintendent and District leaders Participants: Building leaders Frequency: Monthly Intended Outcome: To set expectations and monitor progress.
2018-09-18 | 2018-05-19 | District leaders will identify curriculum learning priorities to observe when conducting weekly Learning Walks to provide building principals with clear feedback that informs their classroom visitations and PLC meeting. Responsible: District leaders Participants: District leaders and building leaders Frequency: Monthly Intended Outcome: To increase consistency across district in all grade and content areas.

## Tenet 4
Tenet 4: Teacher Practices and Decisions |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 4.1 - The district works collaboratively with the school to provide opportunities and supports for teachers to develop strategies and practices and addresses effective planning and account for student data, needs, goals, and levels of engagement. | SOP 4.1 - The district works collaboratively with the school to provide opportunities and supports for teachers to develop strategies and practices and addresses effective planning and account for student data, needs, goals, and levels of engagement.
B1. Most Recent DTSDE Review Date: |  | 2018-09-01
B2. DTSDE Review Type: |  | DCIP Planning Document
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | In the 2017-18 school year, the District established a goal for the implementation of the District instructional Look-Fors (Learning Targets, Higher Order Questions, Student Engagement, Checks for Understanding, and Differentiated Instruction) in all K-12 classrooms. The support visit teams' classroom visits indicated a wide disparity in the quality and alignment of learning targets to tasks and assessments across grades and subject areas. While the District has communicated an expectation for explicit teaching, the process in its entirety, which includes teacher modeling, guided practice, and independent practice, is not yet used by all teachers with fidelity across all schools to effectively support and assess student learning. Reviewers also noted that considerable classroom instruction remains largely teacher-directed, although work on engagement strategies is becoming more evident in teacher practice. The District-led support visit also indicated there are few incidences of differentiated instruction to meet the needs of all students. There is a need for the District to support school leaders to ensure that instructional practices and lessons are implemented consistently and with fidelity to these essential elements: aligned to the Common Core Learning Standards, learning targets aligned to task and assessments, higher order thinking skills, engagement strategies and differentiated instruction to meet individual student and small group needs.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, Assistant Superintendent will facilitate any necessary modifications to the Learning Walk Tool and then monitor its implementation and analyze data collected from Learning Walks to support building leaders in the implementation of professional development for teachers targeted to and supportive of the five District-identified instructional practices (The Foundational Five.)
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Data Dashboards of Learning Walk data Informal and formal APPR observations Staff and Student Surveys Reports from external partners
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-18 | 2018-10-18 | The Superintendent and Assistant Superintendent for Curriculum and Instruction will develop the 2018-2019 Professional Development calendar with PLC Associates so school leaders, teachers and District Cabinet members will receive targeted professional development in the areas of student ownership of learning, engagement, differentiation, higher-order thinking (Depth of Knowledge), and formative assessment for deep implementation of explicit instructional strategies in all classrooms Responsible: Assistant Superintendent Participants: Assistant Superintendent with all consultants to the District Frequency: Once Intended Outcome: To ensure a schedule of regular professional development to support school leaders, District Cabinet members, and teachers in the implementation of District-identified instructional initiatives.
2018-09-18 | 2018-10-18 | The Assistant Superintendent will develop a calendar of Principals' Meetings focused on professional development in support of the District-identified instructional practices Responsible: Assistant Superintendent Participants: School leaders, school leadership teams and Cabinet members Frequency: Ongoing Intended Outcomes: To ensure common understanding and calibration of the expectations for rigor and quality of instructional practices.
2018-09-18 | 2018-06-19 | Visitation teams comprised of cross-building leaders will visit classrooms for the purpose of calibration Responsible: Assistant Superintendent Participants: Building leaders, leadership teams and Assistant Superintendent Frequency: Monthly Intended Outcome: To maintain high standards through calibration of rigorous instructional practices across the District.
2018-09-18 | 2018-06-19 | Assistant Superintendent will monitor the data reports that building leaders are sharing with their faculties regarding implementation of instructional practices from the data gathered through the Learning Walk Tool. They will provide feedback to support building leader practices Responsible: Assistant Superintendent Participants: Building leaders and Assistant Superintendent Frequency: Monthly Intended Outcome: To ensure accountability for implementation and support of instructional practice across the district.
2018-01-19 | 2018-06-19 | District Superintendent and Assistant Superintendent will review building leaders APPR observation write-ups to calibrate the scores and feedback for teachers to ensure the accuracy of the score and its alignment with the Learning Walk data Responsible: Superintendent and Assistant Superintendent Participants: Building leaders, Superintendent and Assistant Superintendents Frequency: Twice a year Intended Outcome: Accuracy of evidence-based scoring and alignment to the data from the Learning Walk Tool.

## Tenet 5
Tenet 5: Student Social and Emotional Developmental Health |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 5.1 - The district creates policy and works collaboratively with the school to provide opportunities and resources that positively support students' social and emotional developmental health. | SOP 5.1 - The district creates policy and works collaboratively with the school to provide opportunities and resources that positively support students' social and emotional developmental health.
B1. Most Recent DTSDE Review Date: |  | 2018-09-01
B2. DTSDE Review Type: |  | DCIP Planning Document
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | The District drafted an RtI Plan during the 2017-18 school year. However, this plan was not finalized or shared with the high school leaders for implementation. In the 2018-19 Middle School SCEP, it was identified the need for a more systematic process and communication of roles and responsibilities for full implementation of an behavioral RtI plan. The District-Led support visits indicated that the middle school leadership, Student Support Services and faculty should add a second tier to the Response to Intervention (RtI) system. Currently, there is inconsistent understanding across the District relative to the root causes of behavioral needs and interventions to address those needs. In order to ensure the social, emotional, learning and academic needs of all students are met, the District needs to refine and share a formal District-wide RTI written plan which supports and sustains student social emotional learning and academic success. This plan should be based upon research-based best practices in order to better understand the SEDH needs and behaviors and their root causes and include a monitoring system to assess the impact of the program.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, the District will establish a tiered model for RtI in the high school and set the parameters and identify foundational beliefs about SEDH needs, including root causes for behavioral needs, and revise the current RtI process to address these beliefs that includes a monitoring system to collect data and assess the impact of interventions to reduce district SEDH referrals by minimally, 15% for the entire district.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Attendance data CSE referrals Suspension data Credit accrual Graduation rate
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-18 | 2018-01-19 | The District will review the District RtI Plans and make additions as needed to identify tiered supports, identification processes and monitoring for SEDH and attendance support in order to support schools to address student risk-factors impacting their academic success in school Responsible: Assistant Superintendent for Instruction and Director of Special Education Participants: Assistant Superintendent for Instruction, Director of Special Education and building leaders Frequency: Several meetings Intended Outcome: To ensure a consistent process in place to address risk factors for students.
2018-09-18 | 2018-06-19 | The District leaders will develop/identify protocols for collection and monitoring of building-level SEDH data (attendance, discipline, suspension, CSE referrals, credit accrual, etc.) that is broken down by grade level and sub-groups in order to address and intervene when individual or larger group data indicates a response to improve SEDH and correlated student achievement Responsible: Assistant Superintendent for Instruction and Director of Special Education Participants: Assistant Superintendent for Instruction, Director of Special Education, building leaders and leadership teams Frequency: Monthly Intended Outcome: To monitor and adjust resources to buildings to support SEDH programs.
2018-09-18 | 2018-06-19 | The Assistant Superintendent for Curriculum and Instruction, the Director for Special Education and school leaders will quarterly review internal school and external agency evidence of impact supporting students at-risk in order to make necessary collaborative adjustments to increase effectiveness Responsible: Assistant Superintendent for Instruction and Director of Special Education Participants: Community partners and Assistant Superintendent for Instruction and Director of Special Education Frequency: Quarterly Intended Outcome: Increase the effectiveness of supports internally and externally.
2018-04-19 | 2018-05-19 | The Assistant Superintendent will identify 3-5 survey questions from the student and teacher surveys related to efficacy/student well-being to monitor progress toward meeting SEDH needs Responsible: Assistant Superintendent and Director of Special Education Participants: Assistant Superintendent, Director of Special Education and building leaders Frequency: Once Intended Outcome: To increase the number of teachers and students responding at the Asset Level of 75% agreement on the selected items.

## Tenet 6
Tenet 6: Family and Community Engagement |  |  | REVIEWER FEEDBACK
A. Statement of Practice Addressed: |  | SOP 6.1 - The district has a comprehensive family and community engagement strategic plan that states the expectations around creating and sustaining a welcoming environment for families, reciprocal communication, and establishing partnerships with community organizations and families. | SOP 6.1 - The district has a comprehensive family and community engagement strategic plan that states the expectations around creating and sustaining a welcoming environment for families, reciprocal communication, and establishing partnerships with community organizations and families.
B1. Most Recent DTSDE Review Date: |  | 2018-09-01
B2. DTSDE Review Type: |  | DCIP Planning Document
REVIEWER FEEDBACK ON NEEDS/DATA SOURCES
C1. Gap Statement: Create a clear and concise statement that addresses the primary gap(s) to be addressed. This statement should be based on a comprehensive needs assessment. Be sure to incorporate feedback from the rationale of the most recent DTSDE review and other applicable data. |  | During the District-Led support visit, regular parent involvement and communication was identified as a concern that all school leaders continue to work on. One of the areas identified was the difficulty in clear communication to parents. Parents in focus groups said they do not always receive clear communications from schools (ex., report cards and assessment information). A culture of partnership between school and family needs to be strengthened through opportunities to educate families on strategies to best support their children through a variety of venues. There is a need for consistent, sustained interaction between school and home.
REVIEWER FEEDBACK ON SMART GOAL/LEADING INDICATORS
D1. SMART Goal: Create a goal that directly addresses the Gap Statement. The goal should be written as Specific, Measurable, Ambitious, Results-oriented, and Timely. |  | By June 2019, the parent response rate on the Family Engagement Survey for each school will be at greater than 50% and the three identified benchmarks (#41 Actively engages our family; #44 Provides programs for families; #50 Families feel connected to our school) will achieve Asset Level.
D2. Leading Indicator(s): Identify the specific indicators that will be used to monitor progress toward the goal. |  | Family Engagement Survey Exit tickets from parent engagement activities
E1. Start Date: Identify the projected start date for each activity. | E2. End Date: Identify the projected end date for each activity. | E3. Action Plan: Detail each action that will take place in order to achieve the identified SMART Goal. Alignment between the Action Plan, SMART Goal, and Gap Statement should be clear. Specifically describe what each planned activity is and what is expected to look different as a result of the activity; who will be responsible for completing each activity; who will participate in each activity; how often each activity will take place; and what the district will look at to determine if implementation is successful. Do not combine multiple activities into a single cell; each activity should be written in its own cell. | REVIEWER FEEDBACK ON ACTIVITIES
2018-09-18 | 2018-05-19 | The Assistant Superintendent working with building leaders will plan and implement parent workshops to support understanding of the ELA, Math, and Science curriculum as well as the principles of efficacy being implemented at all schools Responsible: Assistant Superintendent Participants: Assistant Superintendent, building leaders, parents Frequency: Multiple times throughout the year Intended Outcome: To increase parent understanding and partnership in their students' learning.
2018-09-18 | 2018-06-19 | The Superintendent and District Cabinet will analyze data relative to website usage, parent surveys, attendance at school functions, etc. to plan strategies for strengthening communication and involvement of parents in District activities Responsible: Assistant Superintendent and Cabinet Participants: Cabinet and building leaders Frequency: Quarterly Intended Outcome: To increase active parent involvement within the District.
2018-09-18 | 2018-11-18 | The Assistant Superintendent working with the building leaders will identify strategies that align to the survey questions identified (41, 44 and 50) to focus on in work with parents. Responsible: Assistant Superintendent Participants: Assistant Superintendent and building leaders Frequency: 2x/year Intended Outcome: To increase positive responses at the agree or strongly agree levels.
2018-04-18 | 2018-05-19 | Building leaders will implement surveys with the questions identified to determine the impact of parent engagement strategies implemented during the year Responsible: Building leaders Participants: Parents Frequency: 1x/year full survey with intermittent "spot checks" Intended Outcome: To assess the progress towards the identified goals.
2018-09-18 | 2018-06-19 | Assistant Superintendent and high school building leaders will work with together to plan, communicate and implement parent workshops to support understanding of changes to the curriculum in Math, ELA, Science and Social Studies as well as the principles of efficacy being implemented Responsible: Assistant Superintendent Participants: Assistant Superintendent, building leaders, parents Frequency: Multiple times/year Intended Outcome: to increase parent understanding and partnership in their students' learning.
2018-09-18 | 2018-06-19 | Assistant Superintendent will meet with building leaders to monitor and provide feedback regarding the communication with parents, planned activities with parents, and review the data of progress towards the three identified questions Responsible: Assistant Superintendent and building leaders Participants: Assistant Superintendent and building leaders Frequency: Quarterly Intended Outcome: To increase parent communication and participation in school activities and their child's learning.

## AllocationPlan-Improvement
Financial Allocation Plan - Improvement
Improvement Set-Aside Budget Summary
District | Accountability Status | Amount of Funds Allocated for District-Level Improvement
Focus District
Name of Priority/Focus School | Accountability Status | Amount of Funds Allocated for School-Level Improvement
DISTRICT / BUILDING TOTALS |  | 0

## SI Set Aside Rates (hidden)
School Improvement Set Aside Rate based on count of all schools
LEA BEDS | LEA NAME | All Schools | # of Priority & Focus Schools (minimum required) | % of identified schools | Required Set Aside % | Title III Set Aside required | Percentage of identified schools | Required Set-Aside rate
010100010000 | ALBANY CITY SD | 15 | 13 | 86.67% | 15% |  | Less than 30% | 5%
270100010000 | AMSTERDAM CITY SD | 6 | 5 | 83.33% | 15% |  | 30-34% | 6%
050100010000 | AUBURN CITY SD | 7 | 6 | 85.71% | 15% |  | 35-39% | 7%
030200010000 | BINGHAMTON CITY SD | 10 | 9 | 90% | 15% |  | 40-44% | 8%
062301040000 | BROCTON CSD | 2 | 0 | 0% | 5% |  | 45-49% | 9%
580203020000 | BROOKHAVEN-COMSEWOGUE UFSD | 6 | 0 | 0% | 5% |  | 50-54% | 10%
490202040000 | BRUNSWICK CSD (BRITTONKILL) | 2 | 1 | 50% | 10% |  | 55-59% | 11%
161601040000 | BRUSHTON-MOIRA CSD | 2 | 0 | 0% | 5% |  | 60-64% | 12%
140600010000 | BUFFALO CITY SD | 56 | 35 | 62.5% | 12% |  | 65-69% | 13%
222201060000 | CARTHAGE CSD | 5 | 1 | 20% | 5% |  | 70-74% | 14%
060401040000 | CASSADAGA VALLEY CSD | 2 | 0 | 0% | 5% |  | 75% or more | 15%
190401060000 | CATSKILL CSD | 3 | 3 | 100% | 15%
580513030000 | CENTRAL ISLIP UFSD | 8 | 4 | 50% | 10%
120401040000 | CHARLOTTE VALLEY CSD | 1 | 1 | 100% | 15%
110101040000 | CINCINNATUS CSD | 3 | 1 | 33.33% | 6%
650301040000 | CLYDE-SAVANNAH CSD | 3 | 1 | 33.33% | 6%
010500010000 | COHOES CITY SD | 5 | 0 | 0% | 5%
110200010000 | CORTLAND CITY SD | 6 | 2 | 33.33% | 6%
610301060000 | DRYDEN CSD | 5 | 2 | 40% | 8%
060800010000 | DUNKIRK CITY SD | 6 | 4 | 66.67% | 13%
500402060000 | EAST RAMAPO CSD (SPRING VALLEY) | 14 | 8 | 57.14% | 11%
180901040000 | ELBA CSD | 2 | 0 | 0% | 5%
070600010000 | ELMIRA CITY SD | 11 | 11 | 100% | 15%
590501060000 | FALLSBURG CSD | 2 | 1 | 50% | 10%
021601040000 | FRIENDSHIP CSD | 1 | 1 | 100% | 15%
460500010000 | FULTON CITY SD | 6 | 1 | 16.67% | 5%
430700010000 | GENEVA CITY SD | 4 | 3 | 75% | 15%
081401040000 | GEORGETOWN-SOUTH OTSELIC CSD | 1 | 1 | 100% | 15%
630300010000 | GLENS FALLS CITY SD | 5 | 1 | 20% | 5%
630918080000 | GLENS FALLS COMN SD | 1 | 0 | 0% | 5%
170500010000 | GLOVERSVILLE CITY SD | 6 | 4 | 66.67% | 13%
511101060000 | GOUVERNEUR CSD | 3 | 1 | 33.33% | 6%
042801060000 | GOWANDA CSD | 3 | 1 | 33.33% | 6%
010701030000 | GREEN ISLAND UFSD | 1 | 1 | 100% | 15%
610501040000 | GROTON CSD | 2 | 1 | 50% | 10%
250701040000 | HAMILTON CSD | 2 | 0 | 0% | 5%
460701040000 | HANNIBAL CSD | 3 | 3 | 100% | 15%
230301040000 | HARRISVILLE CSD | 2 | 0 | 0% | 5%
280201030000 | HEMPSTEAD UFSD | 10 | 7 | 70% | 14%
511301040000 | HERMON-DEKALB CSD | 1 | 1 | 100% | 15%
061700010000 | JAMESTOWN CITY SD | 9 | 5 | 55.56% | 11%
540901040000 | JEFFERSON CSD | 1 | 1 | 100% | 15%
031502060000 | JOHNSON CITY CSD | 4 | 2 | 50% | 10%
620600010000 | KINGSTON CITY SD | 10 | 4 | 40% | 8%
420807040000 | LAFAYETTE CSD | 3 | 0 | 0% | 5%
590901060000 | LIBERTY CSD | 2 | 2 | 100% | 15%
161501060000 | MALONE CSD | 5 | 2 | 40% | 8%
121401040000 | MARGARETVILLE CSD | 1 | 1 | 100% | 15%
541001040000 | MIDDLEBURGH CSD | 2 | 1 | 50% | 10%
051301040000 | MORAVIA CSD | 2 | 0 | 0% | 5%
240901040000 | MT MORRIS CSD | 2 | 1 | 50% | 10%
660900010000 | MT VERNON SCHOOL DISTRICT | 16 | 10 | 62.5% | 12%
650101060000 | NEWARK CSD | 5 | 2 | 40% | 8%
441600010000 | NEWBURGH CITY SD | 12 | 6 | 50% | 10%
400800010000 | NIAGARA FALLS CITY SD | 11 | 7 | 63.64% | 12%
651501060000 | NORTH ROSE-WOLCOTT CSD | 3 | 1 | 33.33% | 6%
170901040000 | NORTHVILLE CSD | 2 | 1 | 50% | 10%
411504020000 | NY MILLS UFSD | 2 | 0 | 0% | 5%
550101040000 | ODESSA-MONTOUR CSD | 3 | 0 | 0% | 5%
661500010000 | PEEKSKILL CITY SD | 6 | 3 | 50% | 10%
680601060000 | PENN YAN CSD | 3 | 1 | 33.33% | 6%
091200010000 | PLATTSBURGH CITY SD | 5 | 2 | 40% | 8%
441800050000 | PORT JERVIS CITY SD | 4 | 1 | 25% | 5%
131500010000 | POUGHKEEPSIE CITY SD | 7 | 6 | 85.71% | 15%
580602040000 | RIVERHEAD CSD | 7 | 6 | 85.71% | 15%
261600010000 | ROCHESTER CITY SD | 51 | 41 | 80.39% | 15%
043200050000 | SALAMANCA CITY SD | 3 | 2 | 66.67% | 13%
161201040000 | SALMON RIVER CSD | 4 | 1 | 25% | 5%
530600010000 | SCHENECTADY CITY SD | 17 | 14 | 82.35% | 15%
121601060000 | SIDNEY CSD | 3 | 0 | 0% | 5%
061501040000 | SILVER CREEK CSD | 3 | 0 | 0% | 5%
651201060000 | SODUS CSD | 3 | 1 | 33.33% | 6%
421800010000 | SYRACUSE CITY SD | 33 | 24 | 72.73% | 14%
491700010000 | TROY CITY SD | 7 | 2 | 28.57% | 5%
412300010000 | UTICA CITY SD | 13 | 7 | 53.85% | 10%
121901040000 | WALTON CSD | 3 | 2 | 66.67% | 13%
600101060000 | WAVERLY CSD | 5 | 1 | 20% | 5%
280401030000 | WESTBURY UFSD | 6 | 1 | 16.67% | 5%
262001040000 | WHEATLAND-CHILI CSD | 2 | 0 | 0% | 5%
170301020000 | WHEELERVILLE UFSD | 1 | 1 | 100% | 15%
472506040000 | WORCESTER CSD | 1 | 1 | 100% | 15%
580109020000 | WYANDANCH UFSD | 4 | 4 | 100% | 15%
662300010000 | YONKERS CITY SD | 39 | 10 | 25.64% | 5%
|  | 558 | 311